## Sheet1
Procurement Start Date | Project / Purchase | Manager | Deadlines / Targets | Budget | Procurement Route | Quality | Price | Comments
2019-03-01 | Area 1 - Backcourts WORKS (EF) | Eddy Ferguson | ESPD - April 19 | 900000 | Dual Stage Procedure | 60% | 40%
Committee Approval - June 19
2019-11-01 | Area 2 - Backcourts DESIGN (EF) | Eddy Ferguson | ESPD - December 19 | 50000 | Dual Stage Procedure | 70% | 30%
Quality and Price Scoring - January 20
Committee Approval - February 20
2020-05-01 | Area 2 - Backcourts WORKS (EF) | Eddy Ferguson | ESPD - June 20 | 621000 | Dual Stage Procedure | 60% | 40%
Quality and Price Scoring - August 20
Committee Approval - September 20
2019-02-01 | Asbestos Surveys | John King | ESPD - 15th March 19 | 40000 | Dual Stage Procedure | 70% | 30%
Spec to Contractors - 19th April 19
Committee Approval - June 19
2019-05-01 | Thistle Soft Surface Replacement | John King | Quick Quote issued - June 19 | 15000 | Quick Quote | QQ | QQ
Install July 19
2019-04-01 | Office Furniture Replacement | David Robb | Quick Quote issued - May 19 | 12000 | Quick Quote | QQ | QQ
Committee Aproval - June 19
2019-07-01 | Tenant Satisfaction Survey | Jacqui O'Rourke | Quick Quote issued - August 19 | 8000 | Quick Quote + Quality Assessment | 60% | 40%
Work Commences - October 19
2019-09-01 | Internal Audit | Jacqui O'Rourke | Quick Quote issued - August 19 | 11000 | Quick Quote + Quality Assessment | 60% | 40%
Committee Approval - September 19
2019-06-01 | Rogerfield Environmentals Feasibility Study | Eddy Ferguson | Quick Quote issued - July 19 | 10000 | Quick Quote + Quality Assessment | 70% | 30%
Committee Approval - August 19
2019-06-01 | New Parking Provision Feasibility Study | David Robb | Quick Quote issued - July 19 | 10000 | Quick Quote + Quality Assessment | 60% | 40%
Committee Approval - August 19
2019-07-01 | Stock Condition Survey | John King | ESPD - August 19 | 25000 | Dual Stage Procedure | 70% | 30%
Committee Approval - September 19
2020-04-01 | External Painterwork | John King | ESPD - April/May 20 | 100000 | Dual Stage Procedure | 60% | 40%
Committee Approval - August 20
2020-05-01 | Metering of District Heating System CONSULTANCY | John King | ESPD - April/May 20 | 20000 | Dual Stage Procedure | 70% | 30%
Committee Approval - August 20
2020-09-01 | Metering of District Heating System INSTALLATION | John King | ESPD - Oct 20 | 100000 | Dual Stage Procedure | 60% | 40%
Committee Approval - January 21
2019-05-01 | Rent Harmonisation Feasibility Study | John King | ESPD - June 19 | 10000 | Dual Stage Procedure | 70% | 30%
Committee Approval - september 19
2019-02-01 | Medical Adaptations 20 | John King | Quick quote - March 19 | 10000 | Quick Quote | QQ | QQ
2020-02-01 | Medical Adaptations 21 | John King | Quick quote - March 20 | 10000 | Quick Quote | QQ | QQ
2021-02-01 | Medical Adaptations 22 | John King | Quick quote - March 21 | 10000 | Quick Quote | QQ | QQ
2019-02-01 | Ad Hoc Boiler Replacements 20 | John King | Quick quote - March 19 | 10000 | Quick Quote | QQ | QQ
2020-02-01 | Ad Hoc Boiler Replacements 21 | John King | Quick quote - March 20 | 10000 | Quick Quote | QQ | QQ
2021-02-01 | Ad Hoc Boiler Replacements 22 | John King | Quick quote - March 21 | 10000 | Quick Quote | QQ | QQ